## Instructions
Introduction
Please update the 'Workplan Template' tab of this workbook. Once complete, upload this workbook to your application in the SPEED portal.
An example of a complete workplan has been provided in the 'Example Workplan Template' tab.
This template must be completed and submitted on the SPEED portal before the application deadline.
Please do not add additional months to the 'Workplan Template'.
Please only enter information into white cells.
If you have any questions regarding completing this template, please email speed@esbprogram.ca.
Instructions
1. In the 'Workplan Template' tab, please enter a short description of key milestones (e.g., contract signed) in column A. Information should be added in the white cells.
2. In column B, please provide a description of the tasks required to complete the milestone as well as the start and completion date. Information should be added in the white cells.
3. Between columns F - O, please copy and paste the star into the corresponding month the milestone will complete and use highlighting to show the period where all associated tasks are completed.
For example, if you are creating a milestone for construction and you expect construction to start in September and end in October, you would highlight both September and October in yellow.
You can then copy and paste the star into the month of October. See the 'Example Workplan Template' tab, row 21 for an example.
4. Please do not enter any information in columns C - E as ERA will only provide funding decision notifications in June 2022. If you want to include information on work that was completed prior to June 2022, you can enter that information in column B.
5. If required, you can add additional milestones beyond row 26.
6. Please note that all projects must be completed and submit the post-project application by March 31, 2023.

## Workplan Template
SPEED WORK PLAN TEMPLATE
Legend: -Cells with a star (★) indicate completion of a Milestone task -Yellow highlighted cells indicate tasks start and end dates
MILESTONE | Tasks
|  | Calendar Year 1 - 2022 | [9 empty] | Calendar Year 2 - 2023
|  | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR
| Description of task(s) Please provide sufficient detail to explain the steps required to complete the Milestone. Target dates should be added in parenthesis where possible | Calendar Year 1 - 2022 MAR: Application Submission Period; Calendar Year 1 - 2022 MAY: ERA Application Review Period; Calendar Year 1 - 2022 JUN: LIFE OF PROJECT (MAXIMUM 10 MONTHS)
MILESTONE 1: Example
Contract between Applicant and Eligible Contractor signed. (Target June XX, '22) | bar: Calendar Year 1 - 2022 MAR to Calendar Year 1 - 2022 JUN
MILESTONE 2:
MILESTONE 3:
MILESTONE 4:
MILESTONE 5:
MILESTONE 6:
MILESTONE 7:
MILESTONE 8:
MILESTONE 9:
MILESTONE 10:

## Example Workplan Template
SPEED WORK PLAN TEMPLATE EXAMPLE
Legend: -Cells with a star (★) indicate completion of a Milestone task -Yellow highlighted cells indicate tasks start and end dates
Please note that this is a template and that the information provided below is for illustrative purposes only. The work plan submitted as part of your application must reflect exact information from your project.
MILESTONE | Tasks
|  | Calendar Year 1 - 2022 | [9 empty] | Calendar Year 2 - 2023
|  | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR
| Description of task(s) Please provide sufficient detail to explain the steps required to complete the Milestone. Target dates should be added in parenthesis where possible | Calendar Year 1 - 2022 MAR: Application Submission Period; Calendar Year 1 - 2022 MAY: ERA Application Review Period; Calendar Year 1 - 2022 JUN: LIFE OF PROJECT (MAXIMUM 10 MONTHS)
MILESTONE 1: Contract signed
Contract between Applicant and Eligible Contractor signed. (Target June 15, '22) | bar: Calendar Year 1 - 2022 JUN
MILESTONE 2: Deposit paid
Applicant has paid deposit to Eligible Contractor, equal to 25% of total project cost. (Target June 20, '22) | bar: Calendar Year 1 - 2022 JUN
MILESTONE 3: Equipment ordered
Partial order of parts required for Engine Upgrade: Heads, pistons, intercooler/turbo. (Target July 15, '22) | bar: Calendar Year 1 - 2022 JUL
MILESTONE 4: Equipment paid
Remaining order of parts required for Engine Upgrade: Camshaft, fuel system, combustion system, control system. | bar: Calendar Year 1 - 2022 JUL
MILESTONE 5: Permits secured
Secure permits as required to complete project. | bar: Calendar Year 1 - 2022 JUL
MILESTONE 6: Equipment on site
Parts delivered on site in preparation for installation | bar: Calendar Year 1 - 2022 AUG
MILESTONE 7: Construction/installation
Construction of Engine Upgrade (Sep - Oct, '22) | bar: Calendar Year 1 - 2022 SEP to Calendar Year 1 - 2022 OCT
MILESTONE 8: Submit post-project application to ERA
Submit post-project application to ERA, including all required information as outlined in the Program Guidelines. | bar: Calendar Year 1 - 2022 OCT
MILESTONE 9: Balance of invoice paid to Eligible Contractor
Remaining 75% of project costs paid to Eligible Contractor. | bar: Calendar Year 1 - 2022 NOV
MILESTONE 10: Receive Project Incentive from ERA
Submit Post-Project information to ERA in Dec '22. Receive Project Incentive in Jan '23 | bar: Calendar Year 1 - 2022 DEC to Calendar Year 2 - 2023 JAN